## Active Applications
SN# | Application Name | Project Manager | Team Leader | Project Coordinator | Project Team Member | Average no. of Hours for Support (per Month) |  |  |  |  | Average no. of Hours for Development / Enhancement (per Month)
[6 empty] | Anwar | Navas | Elyza | Thansi | Abdullah | Anwar | Navas | Elyza | Thansi | Abdullah
1 | CRM | Ibrahem | Navas | Elyza | Anwar/Thansi/Abdullah | 20 | 50 | 15 |  | 30 | 50 | 60 |  |  | 70
2 | Site Survey | Ibrahem | Navas | Elyza | Anwar/Thansi/Abdullah | 1 | 4 |  |  | 5 | 1 | 4 |  |  | 5
3 | To Do | Ibrahem | Thansi | Elyza | Anwar/Abdullah | 2 |  | 8 |  |  | 2
4 | KPI | Ibrahem | Anwar | Elyza | Navas | 17 | 4 |  |  |  | 50 | 6
5 | Quotation | Ibrahem | Navas | Elyza | Abduallah |  | 30 |  |  |  |  | 25
6 | Facility Management | Ibrahem | Anwar | Elyza | Thansi/Abdullah | 9 |  |  |  |  | 8
7 | Purchase | Ibrahem | Anwar | Elyza | Thansi/Abdullah | 9 | 3 |  |  |  | 8
8 | Passive Fire | Ibrahem | Thansi | Elyza | Abdullah
9 | Fire Ductwork | Ibrahem | Thansi | Elyza | Abdullah
10 | Suggestions | Ibrahem | Thansi | Elyza | Abdullah
11 | Zylab | Ibrahem | Elyza | Elyza | Ibrahem |  |  | 80
12 | Qlikview | Ibrahem | Ibrahem | Elyza | Ibrahem
13 | EGRC | Ibrahem | Elyza | Elyza | Ibrahem |  |  | 5
14 | SSHR | Ibrahem | Elyza | Elyza | Navas/Anwar | 2 | 2 | 20 |  |  | 1

## On Going Projects
SN# | Application Name | Project Manager | Team Leader | Project Coordinator | Project Team Member | Actual Start Date | No. of days | Due Date | General Remarks | Progress (%)
1 | New Activity | Ibrahem | Anwar | Elyza |  | 2023-05-30 | 10 | 2023-06-09
5 | CRM Admin Updates | Ibrahem |  | Elyza |  |  |  | 0
6 | SO/LOI | Ibrahem |  | Elyza |  |  |  | 0
7 | RMA | Ibrahem | Abdullah | Elyza | Thansi | 2023-04-30 | 30 | 2023-06-05 | Released | 100%
8 | Collection | Ibrahem | Anwar | Elyza | Abdullah |  |  | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
Formulas:
Due Date = [Actual Start Date]+[No. of days]

## Planned Projects
SN# | Application Name | Project Manager | Team Leader | Project Coordinator | Project Team Member | Expected Starting Date | Expected No. of days | Due Date
1 | SSHR Migration | Ibrahem | Anwar | Elyza | Navas | 2023-06-01 | 10 | 2023-06-11
2 | HSE Migration | Ibrahem |  | Elyza |  |  |  | 0
3 | Recruitment | Ibrahem |  | Elyza |  |  |  | 0
4 | Handing Over | Ibrahem |  | Elyza |  |  |  | 0
5 | Bidders | Ibrahem |  | Elyza |  |  |  | 0
6 | E-connect Admin | Ibrahem |  | Elyza |  |  |  | 0
7 | Facility Management | Ibrahem |  | Elyza |  |  |  | 0
Formulas:
Due Date = [Expected Starting Date]+[Expected No. of days]